## Target Scores
Level | Points required
Pass (all mandatory) | 100
1 star | 225
2 stars | 350
3 stars | 475
Points achieved in 2018-2020 | 265
Points targeted for 2020-2022 | 350
Additional points needed for target | 85
Points if all actions are achieved | 395
Points of current complete/in progress actions | 220
Points of current complete/in progress, plus those that are in planning | 320

## 2020-22
Fairtrade University SMART Action Plan
King's College London & KCLSU
Key
Completed
In progress
Not started
Action | Key | Criteria reference | Points value | Specific | Measurable | Appropriate | Realistic | Time | Who is responsible | Status | Notes - June 2021 | Notes - November 2021 | Notes - January 2022
Continue regular meetings of Fairtrade and Sustainable Food Steering Group |  | MN001 | 5 | Group to meet every 3 months | Track group attendance | Related to mandatory criteria MN001 | Yes | Every 3 months | Sustainability Team | Ongoing |  | Meetings continue - all for 2021/22 sent out | Meetings continue - also discussed Fairtrade at the King's CAN Procurement & Waste Group
Make SMART Action Plan publicly available and update actions every 3 months |  | MN002 | 10 | Update Action Plan every 3 months from approval | Update date on website | Related to mandatory criteria MN002 | Yes | Every 3 months | Sustainability Team | Ongoing |  |  | Updated plan uploaded to website
Approve new Fairtrade Policy |  | MN003 | 10 | Fairtrade Policy to be approved | Availability of new Fairtrade Policy | Related to mandatory criteria MN003 | Yes | 2020-12-01 | Sustainability Team | Complete | New policy approved - waiting for upload | New policy now available on website | No updates
Hold promotion for Fairtrade Fortnight 2021 - meeting before Christmas 2020 |  | MN004 | 10 | Meet with King's Food before Christmas 2020 to discuss plans for promotions | Availability of promotions | Related to mandatory criteria MN004 | Yes | 2021-01-01 | Sustainability Team | Not completed | Students and staff were working from home during Fairtrade Fortnight 2021 - online events were held instead |  | n/a
Hold flagship event for Fairtrade Fortnight 2021 - meeting before Christmas 2020 |  | MN004 |  | Meet with King's Food before Christmas 2020 to discuss plans for event | Number of events being held | Related to mandatory criteria MN004 | Yes | 2021-01-01 | Sustainability Team | Complete | Two events were held: King's Sustainability held a virtual 'Fairtrade Fortnight Launch', and King's Food ran an online Fairtrade baking class |  | n/a
Hold promotion for Fairtrade Fortnight 2022 (21 February - 6 March) |  | MN004 |  | Meet with King's Food towards end of 2021 to discuss | Availability of promotions | Related to mandatory criteria MN004 | Yes | 2022-01-01 | Sustainability Team |  |  | Suggested action: Discuss and coordinate in December 2021 | Meeting in December 2021 not held, but Fairtrade Fortnight planning began and was discussed at King's CAN Procurement & Waste meeting.
Hold flagship event for Fairtrade Fortnight 2022 (21 February - 6 March) |  | MN004 |  | Meet with King's Food towards end of 2021 to discuss | Number of events being held | Related to mandatory criteria MN004 | Yes | 2022-01-01 | Sustainability Team |  |  | Suggested action: Discuss and coordinate in December 2021 | NH is organising a careers event for Fairtrade Fortnight, due to take place on 28/02 - MR also working with Fairtrade Universities Networking Group on potential shared event
Design innovative Fairtrade campaign/event to be held outside Fairtrade Fortnight |  | MN005 | 15 | Plan during 2020-21 academic year, run event first term 2021-22 | Event or campaign happening | Related to mandatory criteria MN005, and II001 | Yes | 2022-12-01 | Sustainability Team |  | Not yet completed | International Coffee Week event held in October by King's Food: coffee supplier came in to speak about their supply chain - another event could be held in Spring 2022 | Sustainable Living Communities focused on SDGs and vegan/zero waste continue in Residences (ethical trade). Visions for the Future event series will have a Procurement & Waste workshop
Monitor number of Fairtrade lines and items sold by King's Food |  | MN006 | 10 | Record number by looking at procurement records and outlet displays once per year | Number of lines and items on sale | Related to mandatory criteria MN006 | Yes | July 2021 and 2022 | Sustainability Team, King's Food |  |  |  | Data to be requested by MR in Spring
Introduce Fairtrade cotton items to KCLSU Arcade shop |  | MN006 |  | Introduce at least one piece of Fairtrade clothing | Number of Fairtrade clothing pieces available | Related to mandatory critiera MN006 | Yes | 2022-01-01 | Sustainability Team, KCLSU |  | Not yet completed | Suggested action: Sustainability and KCLSU to discuss options | MR spoke to KCLSU about potential products and suppliers
Suggest new Fairtrade products in any of the following lines as appropriate: soft drinks, wine or beer (or spirits), health and beauty, savoury snacks and nuts, cut flowers, fruit, cotton face masks |  | MN007 | 10 | Ensure Fairtrade items are available in two of these categories. | Availability of Fairtrade items in two of these categories | Related to mandatory criteria MN007 | Yes | 2022-01-01 | Sustainability Team, King's Food |  |  | Fairtrade soft drinks and savoury snacks should be available | No updates
Design plan for POS material to highlight Fairtrade products, including King's Sport promotions |  | MN008 | 10 | Plan regular product highlights | Number of products highlighted throughout the two years | Related to mandatory criteria MN008 | Yes | Ongoing | King's Food, Sustainability Team |  |  |  | Awaiting Fairtrade Fortnight material
Include Fairtrade questions in Residences survey for move-in 2021, and publish results in Sustainability Report |  | MN009 | 5 | Re-use questions from 2019 survey, also used by NUS | Availability of response data | Related to mandatory criteria MN009 | Yes | 2021-09-01 | Sustainability Team, Residences |  |  |  | Not included in Residences survey, but short survey planned for Fairtrade Fortnight
Include at least one Fairtrade project in the sustainability dissertation list on the website |  | MN010 | 5 | Include at least one Fairtrade project in list, which is now shared with Geography students | Availability of Fairtrade project | Related to mandatory criteria MN010 | Yes | Ongoing | Sustainability Team |  |  |  | Dissertation project list to be reviewed - Fairtrade project to be kept
Include Fairtrade section in annual Environmental Sustainability Report 2019-20 and 2020-21 |  | MN011 | 10 | Include Fairtrade section in addition to Food section | Existence of Fairtrade section in reports | Related to mandatory criteria MN011 | Yes | December 2020, December 2021 | Sustainability Team | Ongoing | Environmental Sustainability Report 2019-20 is delayed, but a section on Fairtrade is being included in the shorter Sustainability Update in its place | Fairtrade section has been included in 2019-20 Environmental Sustainability Update | Fairtrade section planned for 2020/21 report
Publish joint reviewed Fairtrade Policy |  | LD001 | 10 | Fairtrade Policy to be approved before end of 2020 | Availability of updated Fairtrade policy | Related to mandatory criteria MN002, and LD001 and LD002 | Yes | 2020-12-01 | Sustainability Team | Complete | Fairtrade Policy was approved | Fairtrade Policy was published | No updates
Publish joint reviewed Fairtrade Policy |  | LD002 | 10 | Fairtrade Policy to be approved before end of 2020 | Availability of updated Fairtrade policy | Related to mandatory criteria MN002, and LD001 and LD002 | Yes | 2020-12-01 | Sustainability Team | Complete | Fairtrade Policy was approved | Fairtrade Policy was published | No updates
Consider potential positive impact of Fairtrade/trade justice/ethical consumption in King's Climate Action Network discussion |  | LD003 | 10 | Include as potential positive impact in Procurement & Waste group | Discussion notes and outcomes showing Fairtrade/ethical consumption/trade justice | Related to LD003 | Yes | 2021-07-01 | Sustainability Team | Ongoing | Climate Action Network included session on food, as well as discussions about choosing suppliers for sustainability credentials | Food remains one of the strands of the Procurement & Waste group of the King's CAN | Fairtrade discussed at January meeting
Include Fairtrade in Welcome to King's staff sessions, and Welcome Week food sessions 2020 |  | CI001 | 10 | Include Fairtrade in staff inductions and Welcome Week/Fortnight events | Slides from events | Related to CI001 | Yes | 2020-09-01 | Sustainability Team | Complete | Several Welcome Week events were held, and Fairtrade was included where appropriate | Information on Fairtrade University status and Fairtrade was included in 'Introduction to Sustainability' online session - were not able to have Fairtrade chocolate handouts at stalls this year, but spoke about it as part of our commitments/targets | No updates
Include Fairtrade in Welcome to King's staff sessions, and Welcome Week food sessions 2021 |  | CI001 |  | Include Fairtrade in staff inductions and Welcome Week/Fortnight events | Slides from events | Related to CI001 | Yes | 2021-09-01 | Sustainability Team |  |  |  | Fairtrade was mentioned in Welcome sessions 2021
Support a student society on Fairtrade/ethical consumption/trade justice event or campaign |  | CI002 | 5 | Support an event from a group such as Fashion Revolution, Climate Action, EcoSoc, Amnesty | Number of events supported | Related to CI002 | Yes | 2022-04-01 | Sustainability Team |  |  |  | King's Food held a vegan sushi class for Vegan & Vegetarian Society
Find another Fairtrade university to discuss progress with |  | CI006 | 15 | Have a meeting on ideas and collaborations with another Fairtrade University | Number of meetings with another Fairtrade University | Related to CI006 | Yes | 2022-04-01 | Sustainability Team |  |  | Joined Fairtrade Universities Networking Group | MR expressed interest in peer review in networking group - Peer review took place 25/01/22
Regularly update Fairtrade web page |  | CI007 | 5 | Update Fairtrade webpage with current action plan and progress, as well as any other updates | Availability of recent updates | Related to CI007 | Yes | Ongoing | Sustainability Team |  |  |  | No updates
Include regular communications on Fairtrade on social media - at least 1 Tweet and Instagram post per month |  | CI008 | 5 | One monthly post about Fairtrade/trade justice | Availability of posts | Related to CI008 | Yes | Ongoing | Sustainability Team |  |  |  | No updates
Include regular communications on Fairtrade on our blog - at least 1 blog post per academic year |  | CI008 |  | One post about Fairtrade/trade justice per year | Availability of blog posts | Related to CI008 | Yes | Ongoing | Sustainability Team |  |  |  | MR to write blog for Fairtrade Fortnight?
Have Fairtrade leaflets/comms materials at Welcome Fair 2021 |  | CI010 | 10 | Show how King's supports Fairtrade at Welcome Week | Availability of Fairtrade materials at Welcome Fair | Related to CI010 | Yes | 2021-09-01 | Sustainability Team |  |  | Very limited handouts were allowed at Welcome Hubs, and no chocolate like in previous years - pointed to our digital resources and website/blog instead | No updates
Keep Fairtrade criteria in Sustainability Champions workbook |  | PL001 | 5 | Criteria asking Champions to make office coffe/tea Fairtrade or Rainforest Alliance certified | Existence of criteria | Related to PL001 | Yes | Ongoing | Sustainability Team |  |  |  | No updates
Do kitchen and purchasing audit in December 2020/January 2021 |  | PL002 | 10 | New purchasing system should allow easier overview - audit to check raw ingredients (e.g. sugar, cocoa) going into kitchens | Availability of audit report | Related to PL002 | Yes | 2021-01-01 | King's Food | Not started |  |  | Delayed due to staffing issues
Aim to make Fairtrade standard in fruit, juice, tea, coffee, sugar, chocolate - including in kitchens |  | PL002 |  | Inrease number of products/raw ingredients where Fairtrade is standard | Number of Fairtrade products/ingredients | Related to PL002 | Yes | 2022-04-01 | King's Food |  |  |  | Delayed due to staffing issues
Send Fairtrade sales data to Fairtrade Foundation at end of academic year |  | PL003 | 15 | Share data on Fairtrade sales with Fairtrade Foundation | Data sent | Related to PL003 | Yes | August 2021 and August 2022 | Sustainability Team |  |  |  | MR to send data before audit
Review upcoming mini-tenders on an ongoing basis |  | PL004 | 5 | Review Fairtrade criteria for mini-tenders as they come up | Inclusion of Fairtrade criteria in relevant mini-tenders | Related to PL004 | Yes | Ongoing | King's Food, Sustainability Team |  |  |  | Ongoing discussions, and King's Food include Sustainability Team in conversations
Ensure any new outlets have same sourcing policies, and new appropriate Fairtrade products are considered |  | PL005 | 5 | Continue to apply same sourcing policies to any new outlets | Availability of Fairtrade products in new outlets | Related to PL005 | Yes | Ongoing | King's Food |  |  |  | No updates
Fairtrade tea, coffee, sugar continue to be standard when ordering for events |  | PL006 | 10 | Continue to offer Fairtrade as standard for coffee, tea, sugar at events | Availability of Fairtrade products at events | Related to PL006 | Yes | Ongoing | King's Food |  |  |  | No updates
Pick one supplier per academic year to engage with on Fairtrade |  | PL007 | 5 | Engage with one supplier per academic year to enquire about their sourcing and options for Fairtrade | Number of suppliers engaged with | Related to PL007 | Yes | July 2021 and 2022 | King's Food, Sustainability Team |  |  |  | No updates
Audit King's Food uniform purchasing |  | PL008 | 10 | Audit King's Food uniform purchasing, including how many of each items are being bought | Existence of audit report | Related to PL008 | Yes | 2021-07-01 | King's Food |  |  |  | Delayed due to staffing issues
Consider whether there are uniform pieces are available in Fairtrade cotton |  | PL008 |  | Consider whether there could be a switch to Fairtrade cotton for some uniform pieces, e.g. aprons | Number of Fairtrade cotton uniform pieces being bought | Related to PL008 | Yes | 2022-04-01 | King's Food |  |  |  | Delayed - but upcoming, and NH will be involved in conversations
Run at least two Fairtrade promotions per year, including King's Sport |  | PL010 | 5 | Run at least two Fairtrade promotions per year | Number of Fairtrade promotions run | Related to PL010 | Yes | Ongoing | King's Food |  |  |  | To do - organise promotion for Fairtrade Fortnight
Record Fairtrade sales data to show increase - correct for Covid-19 closure |  | PL011 | 15 | Record Fairtrade sales data each academic year and compare | Number of Fairtrade items sold | Related to PL011 | Yes | August 2021 and August 2022 | King's Food, Sustainability Team |  |  |  | MR to request data before audit
Encourage at least one staff member to take part in Global Teach In 2022 |  | RC001 | 10 | Encourage at least one staff member to take part in Global Teach In 2022 | Number of staff members taking part, number of sessions | Related to RC001 | Yes | 2022-02-01 | Sustainability Team |  |  |  | MR posted in King's CAN group, but it is taking place during strike action
Support at least two students in project/coursework/dissertation on Fairtrade, trade justice or ethical consumption |  | RC003 | 5 | Support at least two students on dissertation or coursework | Number of student projects supported | Related to RC003 | Yes | 2022-02-01 | Sustainability Team |  |  |  | No updates - no interest from students on dissertation topic yet
Include project on Fairtrade, trade justice or ethical consumption in Sustainability in Practice in 2021-22 |  | RC003 |  | Include at least one Fairtrade project in Sustainability in Practice project proposals | Availability of Fairtrade-related project in project list | Related to RC003 | Yes | 2021-09-01 | Sustainability Team | Not possible at this stage | Sustainability in Practice module has been paused for 2021-22 | Sustainability in Practice module has been paused for 2021-22 | No updates
Partner with another Fairtrade university for peer audit/review |  | RC004 | 5 | Find another Fairtrade University to peer review | Availability of peer review/audit | Related to RC004 | Yes | 2022-04-01 | Sustainability Team |  |  |  | Completed peer review with other universities on 25/01
Include Fairtrade, trade justice and ethical consumption in next curriculum audit |  | RC005 | 15 | Include Fairtrade, trade justice and ethical consumption in next curriculum audit | Data on Fairtrade/ethical consumption/trade justice in curriculum | Related to RC005 | Yes | 2022-04-01 | Sustainability Team |  |  | Curriculum audit planned in 2021/22, based on SDGs | Curriculum review underway
Record 3 positive outcomes from Fairtrade Award for students, providing evidence |  | OT001 | 20 | Record 3 positive outcomes from Fairtrade Award for students, providing evidence | Availability of Outcome report | Related to OT001 | Yes | 2022-04-01 | Sustainability Team |  |  |  | To be done in Spring
Record 3 positive outcomes from Fairtrade Award for KCLSU, providing evidence |  | OT002 | 20 | Record 3 positive outcomes from Fairtrade Award for KCLSU, providing evidence | Availability of Outcome report | Related to OT001 | Yes | 2022-04-01 | Sustainability Team |  |  |  | To be done in Spring
Record 3 positive outcomes from Fairtrade Award for King's, providing evidence |  | OT003 | 20 | Record 3 positive outcomes from Fairtrade Award for King's, providing evidence | Availability of Outcome report | Related to OT001 | Yes | 2022-04-01 | Sustainability Team |  |  |  | To be done in Spring
Record 3 positive outcomes from Fairtrade Award for wider community, providing evidence |  | OT004 | 20 | Record 3 positive outcomes from Fairtrade Award for wider community, providing evidence | Availability of Outcome report | Related to OT001 | Yes | 2022-04-01 | Sustainability Team |  |  |  | To be done in Spring
Design at least one innovative campaign/event and provide write-up |  | II001 | 15 | Design at least one innovative campaign/event and provide write-up | Number of innovative campaigns/events | Related to II001 and MN011 | Yes | 2022-04-01 | Sustainability Team |  |  |  | To be done in Spring